A4.      PROJECT ORGANIZATION

The Radon Testing Program will be managed and implemented by the Fond du Lac Band of Lake Superior Chippewa, with reliance on an independent laboratory for analytical services.

Fond du Lac Personnel

Environmental Program Manager

- Oversee project

- Assign duties relative to the project

- Review Quality Assurance Project Plan

Environmental Health Specialist:

- Preparation of the Quality Assurance Project Plan (QAPP)

- Prioritization of homes and public buildings to be tested

- Test kit deployment, retrieval, and shipment to the laboratory

- Receipt and evaluation of laboratory data

- Creation and maintenance of a radon database

- Re-test determinations

- Re-test deployment, retrieval and shipment to the laboratory

- Preparation of progress and final reports to the Performance Partnership Grant Project Officer

EPA Technical Contact

- Provides review of Radon Measurement QAPP

Independent Laboratory

- Test kits and laboratory services will be provided by Air Chek, Inc. of Naples, North Carolina. Air Chek, Inc. is a privately held corporation that manufactures and analyzes activated charcoal radon measurement samplers used for measuring radon concentrations in indoor air. The company’s organization and employee responsibilities may be reviewed in the Air Chek, Inc. Standard Operating Procedures and Quality Assurance Plan, which is on-file at EPA Region 5.

A5.      Problem definition/background

The Fond du Lac Indian Reservation is located on approximately 100,000 acres of land adjacent to the city of Cloquet, Minnesota, 20 miles from the western tip of Lake Superior. There are 54,000 acres of forested land, 44,000 acres of wetlands, 96 miles of rivers and streams, and 108 bodies of water totaling 2,850 acres within the Reservation’s boundaries. The Reservation is home to the Fond du Lac Band of Lake Superior Chippewa. Of the 3,850 enrolled band members, approximately 1,800 live on the Reservation.

Radon is a colorless, odorless radioactive gas that is released from the natural breakdown of uranium in soil, rock and, to some extent, water. It is considered to be the second leading cause of lung cancer in the United States, responsible for approximately 21,000 lung cancer deaths per year. In 1993, the U.S. EPA developed the Map of Radon Zones, which identifies areas of high, moderate and low potential for elevated radon levels. The zone delineations are based on criteria including geology, aerial radioactivity, soil permeability, indoor radon measurement data and foundation type. The Fond du Lac Reservation, which lies partially within St. Louis County and partially within Carlton County, is in the Zone 2 category. Zone 2 areas are considered to have moderate potential for radon levels above the EPA’s 4 picoCuries per liter of air (pC/L) action level.

From 2001 through 2007, the Fond du Lac Environmental Program managed a Tribal Radon Project designed to determine the prevalence of radon in Reservation homes and public buildings, and to conduct radon mitigation demonstration projects in homes with elevated radon levels. Over the course of the project, 111 homes and 11 public buildings were tested on a voluntary basis. Approximately 25% of homes tested were found to have radon levels near or above the EPA action level, and 30 homes were mitigated. However, approximately two-thirds of tribally-owned residences on the Reservation were not tested under the program. Radon testing will continue to be offered to residents on a voluntary basis, although mitigation services will not.

A6.      PROJECT/TASK DESCRIPTION

This project involves the measurement of radon within Fond du Lac band member homes and tribal owned public buildings. Buildings will be tested upon request. The measurements will primarily be performed during the late fall and winter months when closed-building conditions generally exist as a normal living condition. Each building will be evaluated through the use of an Air Chek, Inc. short-term (3 to 7 days exposure duration) activated charcoal adsorber test packet. The laboratory results will be compared to the EPA’s recommended action level of 4 pC/L (to provide maximum environmental health protection for Fond du Lac residents, the residential standard will also be applied to public and commercial buildings). Those homes or public buildings that possess analytical results of 4 pC/L or greater will be subject to a follow-up confirmatory test using an Air Chek, Inc. test packet in the same location with identical protocols as the initial measurement. If the average of the two test results remains higher than 4 pC/L, tenants will be advised to consider mitigation.

A7.      PROJECT OBJECTIVES

Problem Statement

Smokers face an increased risk of developing radon-related lung cancer and smoking rates are nearly 10% higher among American Indians/Alaska Natives than among the general population (American Lung Association, June 2007). In addition, radon testing in Fond du Lac homes between 2001 and 2006 indicated that approximately 25% of reservation housing has radon levels that are close to or above 4 pC/L. On-going testing will help protect the health of Fond du Lac Band members and employees.

Decision

The project is intended to continue the assessment of the levels of radon and/or radon decay products in homes and public buildings on the Reservation. The results will be used to provide the Fond du Lac Environmental Program with the necessary information to make informed recommendations to participating homeowners and public building managers regarding indoor air quality and potential mitigation procedures.

Inputs to Decision

Short-term (3 to 7 days exposure duration) activated charcoal test packets will be used to measure the radon concentrations in homes and public buildings. The radon test packets will be obtained from, and analyzed by, Air Chek, Inc. of Naples, North Carolina.

Study Boundaries

The project is limited to participating Band members’ homes and tribal-owned public buildings on or near the Fond du Lac Reservation. At each measurement location, an activated charcoal test packet will be placed two (2) to six (6) feet above the floor in the lowest living area of the home or building. The test packet’s opening will face toward an open area of the room, and will be placed at least four (4) inches from other objects. The detector will be placed at least 12 inches from the outside walls of the building, and no less than 36 inches from any opening in the outside walls, such as windows or doorways.

Decision Rule

If the results of the mitigation measurement exceed the USEPA recommended action level of 4 pC/L, appropriate mitigation strategies will be suggested to the resident or building manager.

Limits on Decision Errors

Homes, offices or buildings that exhibit analytical results that exceed the USEPA recommended action level of 4 pC/L will be offered a second test. All follow-up tests will be conducted using an Air Chek, Inc. test packet in the same location with identical protocols as the initial measurement. If the average of the two results exceeds 4 pC/L, the homeowner or building manager will be notified and appropriate mitigation techniques will be recommended.

Design for Obtaining Data

Tribal-owned public buildings and participating Fond du Lac Band member households will be measured for radon and/or radon decay products.

A8.      SPECIAL TRAINING REQUIREMENTS/CERTIFICATION

The Environmental Health Specialist and the Fond du Lac Air Quality Technician have successfully completed the radon measurement proficiency course offered by the Midwest Universities Radon Consortium at the University of Minnesota, St. Paul.

A9.      DOCUMENTATION AND RECORDS

The Environmental Health Specialist is responsible for ensuring that the most current copy of the QAPP (draft or approved status) is available to project personnel, the EPA Radiation Quality Assurance Coordinator, and the EPA Performance Partnership Grant Project Officer. The current version of the QAPP will be identified in the upper right hand corner of each document page.

The Environmental Health Specialist will ensure that data is recorded appropriately on the test packets and on field data collection sheets, and that the test packets are deployed in sequential order of serial numbers. All entries will be made using indelible ink, with no erasures. If an incorrect entry is recorded, the information will be drawn through with a single strike mark that will be initialed and dated. The Environmental Health Specialist is responsible for the maintenance of all documents, records and laboratory analytical results.

Test Packet Deployment/Retrieval Records

Indelible ink will be used to label all test packets. An in-house field data collection form has been developed for use during the deployment and retrieval of the test packets (an example is on file at EPA Region 5). The form will include the name of the homeowner, address, location of the device, start date and time, stop date and time, the serial number of the test packet, temperature and any additional information that is pertinent to the test site (such as evidence of tampering or whether “closed-building” conditions exist). This documentation will demonstrate that proper sampling protocol was performed in the field.

Sample Tracking Records

Chain-of-custody control will not be used for this project.

Analytical Data

Analytical data will be submitted to the Fond du Lac Environmental Health Specialist by Air Chek, Inc. for evaluation and recommendation for re-test, as appropriate. All data will be kept confidential and shared only with the homeowner or building manager for privacy purposes. The information will be stored in an Excel spreadsheet, which is accessible only to the Environmental Health Specialist.

B1.      SAMPLING METHODS REQUIREMENTS

The indoor air at each structure included in the project will be tested once using an Air Chek, Inc. short-term (3 to 7 day exposure duration) activated charcoal test packet for radon and/or radon decay products. All participants will be reminded to make sure all external doors, windows and vents are kept closed beginning 12 hours before the start of the test period. Placement of the packets will follow the protocols provided by Air Chek, Inc., and the June 1993 EPA document entitled Indoor Radon and Radon Decay Products Measurement Device Protocols (on file at EPA Region 5).

Measurement Device Location Selection

- Each test packet will be placed within the lowest level that contains a room that is used regularly.

- A position should be selected where the detector will not be disturbed during the measurement period and where there is adequate room for the device.

- The test packet should not be placed in areas near drafts caused by heating, ventilation and air conditioning vents, doors, fans and windows. Additionally, areas near excessive heat, such as fireplaces and direct sunlight, and areas of high humidity should be avoided.

- The packet locations should not be less than three (3) feet from windows or other openings in an exterior wall. If there are no openings along the exterior wall, the test device should be placed at least 12 inches from the exterior wall.

- The packet must be placed within the normal breathing zone of two (2) feet to six (6) feet from the floor. It can be placed on a table or shelf, or may be suspended from the ceiling or interior non-masonry wall.

Preparation Of Measurement Device

- All Air Check, Inc. test packets are sealed in cellophane. Check the cellophane packaging for tears, holes, etc. If the packaging has been compromised, record the serial number and the package condition as “damaged” on a field data form. Select the next test packet in sequential order. Check the integrity of the packaging.

- If the packaging is undamaged, record the test packet serial number on a new field data form, along with the homeowner’s name and address.

- Remove the cellophane packaging.

- Using a waterproof pen, record the name and address, test start hour and date on the back of the test packet and on the field data form, as indicated in the Air Chek Test Starting Instructions Sheet (on file at EPA Region 5).

- Record the selected location for the test packet deployment on the field data form.

- With the opening of the test packet pointed up, push the opposite sides of the packet together to make a square, as indicated in the Air Chek Test Starting Instructions Sheet.

- Insert the block of foam into the opening of the packet by holding the block by the plastic tab, inserting it only far enough to match up with the edges of the test packet. Verify that the foam fills the opening and holds the packet open, as indicated in the Air Chek Test Starting Instructions Sheet.

Placement Of Measurement Device

- Do not place the test packet within three feet of another activated charcoal device. (Exception: Two Air Chek, Inc. test packet devices may be placed within four inches of one another for quality control purposes.)

- Place the open end of the packet with the foam facing an open area of the room.

- Verify that the open end of the packet is not obstructed.

Measurement Device Retrieval

- Each test packet will be retrieved no earlier than three (3) days, and no later than seven (7) days, after its deployment.

- Do not remove the test packet from the area until the packet has been sealed.

- Remove and discard the foam and plastic hook from the test packet (use scissors to remove the hook).

- Inspect the area for deviations of conditions that had been noted on the field data form at the time of deployment.

- Record the serial number of the test packet on the field data form.

- Record the test end time hour, day of the month, and average room temperature on the back of the packet in the spaces provided, and on the field data form.

- Fold back the envelope flaps on the test packet. Remove the cover tape from the adhesive strip and seal the envelope flaps together.

- Verify that the packet is sealed air-tight. Repair any tears or unsealed flaps with a small piece of plastic tape or cellophane tape.

- Mail each test packet to Air Chek, Inc. within 24 hours of its retrieval from the test location, following the manufacturer’s directions.

- Record the post office location, date, and time the test packet was mailed on the field data form.

B2.       SAMPLE HANDLING AND CUSTODY REQUIREMENTS

All participant homes and tribal-owned facilities will be tested using a dedicated test packet with a unique, pre-printed serial number for proper identification. All required information will be recorded on each test packet and on field data forms using indelible ink. The Environmental Health Specialist is responsible for the care and custody of the test packet samples, including transport of the exposed test packets to the post office for mailing to Air Chek, Inc. for analyses. Each test packet will be mailed to Air Chek, Inc. within 24 hours of retrieval. Chain-of-custody documentation is not required for this project. Air Chek, Inc. will be responsible for logging and storage of the exposed test packets according to their standard procedures.

B3.       ANALYTICAL METHODS REQUIREMENTS

Air Chek, Inc. will analyze all test packets at their analytical laboratory in Naples, North Carolina. All test packets will be analyzed in accordance with the procedures outlined in the December 15, 1998 document entitled Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors (on file at EPA Region 5).

B4.       QUALITY CONTROL REQUIREMENTS

The quality assurance objectives for this project are to develop and implement procedures for field sampling, laboratory analyses, and reporting that will provide high quality, reliable results. Specific procedures regarding these items are presented in other sections of the QAPP.

Precision

Precision is a measure of the degree to which two or more measurements are in agreement. Field precision is assessed through the collection and measurement of field duplicates or replicates, which will be deployed in circumstances involving more than 50 test kits. Total precision is a measurement of the variability associated with the entire sampling and analytical process. It is evaluated through the analyses of duplicate or replicate field samples and measures the variability introduced by both the laboratory and field operations. One field duplicate test packet will be exposed for every ten primary test packet exposures when more than 50 test kits are deployed. Field duplicates will not be deployed in testing individual homes, unless more than 50 residences are tested at one time.

Duplicate results will be assessed using the relative percent difference (RPD) between duplicate test packet measurement concentrations. For duplicate measurements, the RPD will be calculated as follows:

RPD = (D1-D2) x 100%

(D1 + D2) / 2

where RPD = relative percent difference

D1   = sample value

D2   = duplicate sample value

The objective for the precision of radon concentrations using Air Chek, Inc. test packets at or above 4 pC/L is an average of 10 percent relative difference.

Accuracy

Accuracy is the degree of agreement between an observed value and an accepted reference value. Accuracy in the field is assessed through the adherence to all sample collection, handling, preservation, and holding times. Laboratory accuracy is assessed through the analysis of matrix spikes or standard reference materials, and the determination of percent recoveries. This procedure will be performed by the Air Chek, Inc. laboratory, according to sections 5.0, 9.9 and 12.0 of the Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors document (on file at EPA Region 5).

Representativeness

Representativeness expresses the degree to which data accurately and precisely represent a characteristic of a population, parameter variations at a sampling point, a process condition, or an environmental condition. It is dependent on the proper design of the sampling program and will be satisfied by ensuring that the field sampling plan is followed and that proper sampling techniques are used. The Environmental Health Specialist will ensure that all EPA radon testing protocols for deployment and retrieval of activated charcoal radon detection devices, as summarized in the Section B1, are followed. Representativeness in the laboratory is ensured through the use of proper analytical procedures, analyses of samples within holding times, and analyses and assessment of field duplicate samples when they are used.

Comparability

Comparability is an expression of the confidence with which one data set can be compared with another. It is dependent on the proper design of the sampling program and will be satisfied by ensuring that the field sampling plan is followed and that proper sampling techniques are used. Planned data is comparable when similar sample collection and analytical methods are used and documented in the QAPP. This QAPP addresses comparability by specifying appropriate field methods and presenting the Air Chek, Inc. laboratory protocols in the appended Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors document.

Completeness

Completeness is the amount of valid data obtained compared to the amount that was expected to be obtained under normal conditions. The number of valid results divided by the number of planned data points, expressed as a percentage, determines the completeness of the data set. Completeness for this project is not specified since the number of data points is contingent upon voluntary participation.

B5.       INSTRUMENTATION/EQUIPMENT TESTING, INSPECTION AND                       MAINTENANCE RECORDS

There is no specialized field equipment necessary to implement the test packet deployment/retrieval phase of this project. Each test packet will be evaluated for suitable use prior to deployment as specified in Section B1. The Air Chek, Inc. technical staff will be responsible for all laboratory instrument and equipment tests, inspections and maintenance.

B6.       INSTRUMENT CALIBRATION AND FREQUENCY

Air Chek, Inc. will be responsible for the calibration of all analytical instruments. The calibration procedures may be reviewed in the appended Air Chek, Inc. document entitled Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors.

B7.       INSPECTION/ACCEPTANCE REQURIEMENTS FOR SUPPLIES

Each test packet will be evaluated for suitable use prior to deployment as specified in Section B1. Air Chek, Inc. will be responsible for inspection and acceptance determination of any supplies used in their laboratory.

B8.       DATA MANAGEMENT

An in-house field data form that includes the name of the homeowner or renter, address, location of the device, start date and time, stop date and time, device ID number, temperature and any additional information that is pertinent to the test site (on file at EPA Region 5) will be the initial documentation for all test devices deployed. The information will be transferred to an Excel spreadsheet by the Environmental Health Specialist as the tests are completed. The forms will be bound and kept on file at the Fond du Lac Environmental Program offices.

Analytical data will be submitted to the Environmental Health Specialist by Air Chek, Inc. for evaluation and recommendation for re-testing, as appropriate. The information will be added to the Excel spreadsheet database and the accuracy of previously transferred data will be verified at that time. All data will be kept confidential and will be shared only with the homeowner or building manager for privacy purposes.

C1.       ASSESSMENTS AND RESPONSE ACTIONS

No external audits are planned for this program. The Environmental Health Specialist will ensure that the elements of the QAPP are implemented as prescribed. Assessment of test packet deployment, retrieval, scheduling and data management will be periodically performed via discussions between the Environmental Health Specialist and the Environmental Program Manager. Any need for corrective action will be identified during these reviews and implemented immediately.

All laboratory assessments and corrective actions will be performed by Air Chek, Inc. according to their Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors document.

C2.       REPORTS TO MANAGEMENT

Programmatic and financial status reports will be submitted to the EPA Performance Partnership Grant Project Officer on a quarterly basis, in accordance with the terms and conditions of the grant.

D1.       DATA VALIDATION AND USABILITY

Sections B1 and B2 of this document outline the details necessary for the consistent deployment, retrieval and sample shipment methods. Adherence to the stated protocols will ensure the data’s usability from a field collection standpoint.

Laboratory data validation procedures at Air Chek, Inc. are outlined in the document Standard Operating Procedures and Quality Assurance Plan – Measurements of Indoor Ambient Radon Concentrations Using Activated Charcoal Adsorber Detectors (on file at EPA Region 5). The laboratory will provide notice with, or in lieu of, the analytical results with respect the data’s accuracy or validity. These notices are related to the following conditions noted by the laboratory on receipt of the test packets:

- Time elapsed since close of the test and receipt at the laboratory

- Exposure to excessive moisture

- Exposure to extreme temperatures

- Insufficient information supplied with the test packet

- Improperly sealed test packets

These notices will be reviewed to assess the usability of an individual analytical result.

D2.       RECONCILIATION WITH DATA QUALITY OBJECTIVES

Data quality assessment (DQA) follows the data validation and verification steps. As such, DQA determines how well the validated data can support their intended use. The Environmental Health Specialist will evaluate the data to determine if it will meet the data quality objectives outlined in Section  A7.